Senate Bill 452 (Online Travel Companies) Study

Work Plan

| Action | ### Target Date | ### Completion Date |
| --- | --- | --- |
| ### List of Interested Parties Created | ### May 7, 2010 |  |
| ### Compile data on legislation and court cases in other states | ### May 21, 2010 |  |
| ### Interested Parties Meeting | ### May 27, 2010 |  |
| ### Compile list of issues identified at Interested Parties meeting | ### June 1, 2010 |  |
| ### Revenue Analysis Due | ### July 9, 2010 |  |
| ### Draft Report to Senior Tax Policy Analyst | ### July 19, 2010 |  |
| ### Draft Report to Director, Policy Development Section | ### August 2, 2010 |  |
| ### Draft Report to Assistant Commissioner For Tax Policy | ### August 18, 2010 |  |
| ### Draft Report to Tax Commissioenr | ### September 1, 2010 |  |
| ### Final Report to GA | ### October 1, 2010 |  |