Local Cigarette Tax Enforcement Study (HB 2038 and SB 1085)

Work Plan

| Action | ### Target Date | ### Completion Date |
| --- | --- | --- |
| ### Compile background information | ### April 13, 2011 |  |
| ### Interested Parties Meeting – Clarify Purpose of Working Group, Identify Issues, etc. | ### April 20, 2011 |  |
| ### Compile list of issues identified at Interested Parties meeting | ### April 29, 2011 |  |
| ### Information/Comments from Interested Parties due | ### May 24, 2011 |  |
| ### Interested Parties Meeting #2 – Possible Site Tour | ### July 8, 2011 |  |
| ### Information/Comments from Interested Parties due | ### July 29, 2011 |  |
| ### Draft Report to Interested Parties for Comment | ### September 7, 2011 |  |
| ### Interested Parties Meeting #3 – Discuss Report | ### September 30, 2011 |  |
| ### Interested Parties Comments due | ### September 30, 2011 |  |
| ### Final Draft to Interested Parties for Comments included in Final Report to GA | ### October 21, 2011 |  |
| ### Interested Parties Comments included in Final Report due | ### November 18, 2011 |  |
| ### Final Report to GA | ### December 1, 2011 |  |